## Feature Gap Analysis
TRM Recruitment Platform - Feature Gap Analysis
Comprehensive comparison with top 10 global recruitment platforms
Category | Feature | TRM Status | Rating (1-5) | Priority | Gap Description | Action Item | Estimated Effort
ATS Core | Candidate Pipeline Management | ✅ Has | 3 | Medium | Basic stages, needs customization | Add customizable pipeline stages with drag-drop | 2 weeks
ATS Core | Job Requisition Management | ✅ Has | 3 | Medium | Basic job creation exists | Add approval workflows and budget tracking | 1 week
ATS Core | Application Form Builder | ❌ Missing | 0 | High | No custom application forms | Build drag-drop form builder with validation | 3 weeks
ATS Core | Resume Parsing (AI) | ❌ Missing | 0 | High | No resume parsing capability | Integrate AI resume parser (spaCy/AWS Textract) | 2 weeks
ATS Core | Candidate Scoring/Ranking | ❌ Missing | 0 | High | No scoring system | Implement AI-based candidate matching algorithm | 3 weeks
ATS Core | Interview Scheduling | ✅ Has | 2 | Medium | Basic scheduling exists | Add calendar integration (Google/Outlook) | 2 weeks
ATS Core | Offer Management | ❌ Missing | 0 | High | No offer letter generation | Build offer template system with e-signature | 2 weeks
ATS Core | Onboarding Module | ❌ Missing | 0 | Medium | No onboarding features | Create onboarding checklist and document collection | 3 weeks
CRM | Client/Company Management | ✅ Has | 3 | Low | Basic client tracking | Add client portal and contact history timeline | 2 weeks
CRM | Contact Relationship Tracking | ⚠️ Partial | 2 | Medium | Limited interaction history | Implement full communication tracking | 2 weeks
CRM | Sales Pipeline (Deals) | ✅ Has | 3 | Low | Basic deal stages | Add revenue forecasting and probability scoring | 1 week
CRM | Email Integration | ❌ Missing | 0 | High | No email sync capability | Integrate Gmail/Outlook API for email tracking | 3 weeks
CRM | Email Templates | ❌ Missing | 0 | High | No email templates | Build template library with merge fields | 1 week
CRM | Email Sequences/Automation | ❌ Missing | 0 | High | No automated outreach | Implement drip campaigns and follow-up sequences | 3 weeks
AI/Automation | AI Candidate Matching | ❌ Missing | 0 | High | No AI matching | Build ML model for job-candidate matching | 4 weeks
AI/Automation | Automated Screening | ❌ Missing | 0 | High | No automated screening | Create rule-based screening criteria | 2 weeks
AI/Automation | Chatbot for Candidates | ❌ Missing | 0 | Medium | No chatbot | Implement AI chatbot for FAQ and scheduling | 3 weeks
AI/Automation | Predictive Analytics | ❌ Missing | 0 | Medium | No predictive features | Add ML models for hiring success prediction | 4 weeks
AI/Automation | Workflow Automation | ❌ Missing | 0 | High | Manual workflows only | Build automation triggers and actions | 3 weeks
Analytics | Dashboard Metrics | ✅ Has | 3 | Low | Basic KPIs available | Enhance with real-time data and benchmarks | 1 week
Analytics | Custom Reports Builder | ❌ Missing | 0 | High | No custom reports | Build drag-drop report builder | 3 weeks
Analytics | Time-to-Hire Analytics | ❌ Missing | 0 | High | No time tracking | Add funnel analytics and stage duration | 2 weeks
Analytics | Source Effectiveness | ❌ Missing | 0 | Medium | Basic source tracking | Build source attribution and ROI analysis | 2 weeks
Analytics | Export Options (CSV/PDF) | ❌ Missing | 0 | Medium | No export feature | Add export functionality for all reports | 1 week
Integrations | Job Board Posting | ❌ Missing | 0 | High | No job board integration | Integrate LinkedIn, Indeed, JobNet Myanmar | 2 weeks
Integrations | Calendar Integration | ❌ Missing | 0 | High | No calendar sync | Add Google Calendar and Outlook integration | 2 weeks
Integrations | Video Interview (Zoom) | ❌ Missing | 0 | High | No video integration | Integrate Zoom/Teams for video interviews | 2 weeks
Integrations | Background Check API | ❌ Missing | 0 | Medium | No background check | Integrate with background check providers | 3 weeks
Integrations | HRIS Integration | ❌ Missing | 0 | Medium | No HRIS sync | Build connectors for Workday, BambooHR | 4 weeks
Integrations | Social Media Sourcing | ❌ Missing | 0 | Medium | No social integration | Add LinkedIn and Facebook sourcing | 2 weeks
Security | User Authentication | ⚠️ Partial | 2 | High | Basic role switching only | Implement proper OAuth2/JWT authentication | 2 weeks
Security | Role-Based Access Control | ⚠️ Partial | 2 | High | Basic roles exist | Add granular permissions system | 2 weeks
Security | Two-Factor Authentication | ❌ Missing | 0 | High | No 2FA | Implement TOTP/SMS 2FA | 1 week
Security | Data Encryption | ❌ Missing | 0 | High | No encryption | Implement AES encryption for sensitive data | 1 week
Security | Audit Logs | ❌ Missing | 0 | High | Basic activity only | Build comprehensive audit trail system | 2 weeks
Security | GDPR Compliance | ❌ Missing | 0 | High | No consent management | Add consent forms and data retention policies | 2 weeks
Mobile/UX | Responsive Design | ⚠️ Partial | 2 | Medium | Desktop focused | Implement mobile-first responsive design | 2 weeks
Mobile/UX | Mobile App | ❌ Missing | 0 | Medium | No native app | Build React Native mobile app | 8 weeks
Mobile/UX | Dark Mode | ❌ Missing | 0 | Low | Light mode only | Add dark mode toggle with system preference | 1 week
Mobile/UX | Accessibility (WCAG) | ❌ Missing | 0 | Medium | No accessibility compliance | Implement WCAG 2.1 AA compliance | 3 weeks
Mobile/UX | Search Functionality | ⚠️ Partial | 2 | Medium | Basic search exists | Add advanced filters and full-text search | 2 weeks

## Platform Comparison
Top 10 Recruitment Platforms - Feature Comparison
Feature Category | TRM Platform | Bullhorn | Greenhouse | Lever | Zoho Recruit | Recruiterflow | LinkedIn Recruiter | Jobvite | BambooHR | Recruitee | JazzHR
ATS Core Features | 3 | 5 | 5 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 4
CRM Capabilities | 3 | 5 | 4 | 4 | 5 | 4 | 4 | 3 | 4 | 3 | 3
AI & Automation | 0 | 5 | 4 | 3 | 4 | 5 | 5 | 2 | 3 | 2 | 2
Analytics & Reporting | 3 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3
Integrations | 0 | 5 | 5 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 3
Security & Compliance | 2 | 5 | 5 | 5 | 4 | 5 | 5 | 4 | 4 | 4 | 4
Mobile Experience | 2 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 3
User Experience | 3 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 4
Customization | 2 | 5 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 3
Pricing Value | 5 | 3 | 3 | 4 | 5 | 2 | 2 | 4 | 4 | 4 | 5

## Priority Roadmap
TRM Platform Development Roadmap - Priority Order
Based on feature gap analysis - Top 10 priority items to close first
Priority | Feature | Category | Business Impact | Implementation Steps | Effort | Dependencies | Status
1 | User Authentication (OAuth2/JWT) | Security | CRITICAL - Required for multi-tenant | 1. Set up Auth0/Firebase Auth 2. Implement JWT tokens 3. Add session management 4. Build login/signup UI | 2 weeks | None | Not Started
2 | Resume Parsing (AI) | AI/Automation | HIGH - Saves 80% screening time | 1. Integrate AWS Textract/OCR 2. Build parsing pipeline 3. Map to candidate fields 4. Add batch processing | 2 weeks | Authentication | Not Started
3 | Email Integration | CRM | HIGH - Core recruiter workflow | 1. Set up Gmail/Outlook API 2. Implement OAuth flow 3. Build email sync service 4. Add threading support | 3 weeks | Authentication | Not Started
4 | AI Candidate Matching | AI/Automation | HIGH - 3x faster placements | 1. Design matching algorithm 2. Train ML model 3. Build scoring API 4. Create match UI | 4 weeks | Resume Parsing | Not Started
5 | Job Board Integration | Integrations | HIGH - Expands candidate pool | 1. Research Myanmar job boards 2. Build API connectors 3. Create posting UI 4. Add tracking | 2 weeks | Authentication | Not Started
6 | Calendar Integration | Integrations | MEDIUM - Automates scheduling | 1. Set up Google Calendar API 2. Add Outlook support 3. Build scheduling UI 4. Create reminders | 2 weeks | Authentication | Not Started
7 | Custom Reports Builder | Analytics | MEDIUM - Client deliverables | 1. Design report schema 2. Build query builder 3. Add chart components 4. Create export feature | 3 weeks | None | Not Started
8 | Two-Factor Authentication | Security | MEDIUM - Enterprise requirement | 1. Implement TOTP 2. Add SMS option 3. Build backup codes 4. Create settings UI | 1 week | Authentication | Not Started
9 | Mobile Responsive Design | Mobile/UX | MEDIUM - Field recruiter need | 1. Audit current UI 2. Redesign key pages 3. Test on devices 4. Optimize performance | 2 weeks | None | Not Started
10 | GDPR Compliance | Security | MEDIUM - International clients | 1. Add consent forms 2. Build data export 3. Implement deletion 4. Update privacy policy | 2 weeks | Authentication | Not Started